31 January 2012

Dr Tony Britt

Sheep and Cattle Compensation Funds

FINAL REPORT

Project Number  312429

Project Title Livestock Standstill in Victorian Saleyards

Dear Tony,

This report provides a status update on the stock standstill project funded by the Cattle and sheep compensation funds during 2011.

# BACKGROUND AND SCOPE

The project will be delivered across the Victorian saleyard sector and will include all yards as required and will not be restricted to LSAV member yards only.

By the end of the project, Victorian saleyards will be better prepared to manage their premises when a livestock standstill is in force. Saleyards with effective contingency plans and well informed personnel will play a critical role in preventing the spread of FMD if an outbreak were to occur in Australia.

# SCHEDULE OF WORK

- Two part initial workshop (on 1 day)

This was undertaken between the project manager (Frank White from LEC) and LSAV to scope out the project requirements.

# Create a project liaison committee including representatives from ALPA, LTAV, saleyards and DPI.

This was formed and included representatives from ALPA (Ashley Copping), LSAV (Mark McDonald), the project managers (Frank White and David Pollock), LTAV (Kevin Keegan) and DPI (Malcolm Ramsey). This group meet on two occasions. Initially to discuss the project scope and then to sign off on the final template.

# Review current arrangements for stock standstill (yard plans, NSQA, associations (LSAV, ALPA, LTAV), councils disaster recovery and governmental. Consider current 2003 LSAV/DPI draft plan.

This was undertaken as part of the consultation process with the yards. The initial DPI template was used as the starting point and altered based on industry feedback. A list of all of the yards contacted is listed below. Not all yards took up the opportunity to be part of the project and either had their own plan already in place or were not interested in participating.

NSQA was also consulted in terms of getting their code altered to include a requirement to have an approved stock standstill plan as part of their procedures. This was agreed to by the NSQA executive in late 2011 and will provide further impetus for the rollout to Victorian yards.

# Provide a summary of the current Victorian saleyard status.

This was generated as part of the consultation process. A number of yards with existing plans decided to change to the new template whilst others updated their current plan as they deemed necessary.

# Design a plan in conjunction with industry input (saleyard staff etc) and including the current LSAV/DPI Victorian draft.

This was done following input from the committee and individual saleyards. A copy of the final template is included with this final report.

# Review plan with stakeholders and committee.

Part of the committee and consultation process.

# Provide an implementation plan for individual yards and associations.

This was provided to all participating yards at the end of the project. This included the template and instructions for completing this. Two workshops we also conducted at the LSAV annual conference in August 2011 as a way to prime members to update their respective templates. Three yards requested additional assistance was provided as required.

The final template was also distributed to LSAV associate members in SA and NSW as well as the SA Saleyard Association and ALMA. We are uncertain if either of these organizations has taken up this offer.

# Design an exercise for testing of the plan.

This component of the project was only discussed briefly at the start of the committee process. It was decided to reconsider this option once the template had been distributed and industry uptake was widespread. This component of the budget was not invoiced ($15,000). Subsequently Animal health Australia has been proposing a national stock standstill exercise. LSAV has expressed interest in being involved with this along with DPI. Therefore no further action on this part of the project until the AHA exercise is more fully understood.

# ATTACHMENTS

The following attachments are provided as an adjunct to this summary report.

- List of yards contacted for project.

- Final stock standstill template.

- Stock standstill user guide and schematic (pdf).

# FINAL SUMMARY

The uptake of the new template is not yet complete with a number of yards either still resisting the process or failing to complete their yard plans at this time. LSAV will undertake a further workshop process at its February 24, 2012 saleyard manager’s forum to market the template.

All NSQA yards will need to provide this plan by their next audit which will cover a large percentage of the Victorian yards once combined with the existing completed copies and yards with existing templates. Taken all these factors into consideration it is estimated that around 85% of Victorian yards are currently covered with a stock standstill plan.

Further consideration would need to be made regarding the exercise if the AHA version does not eventuate or does not include Victoria.