Discussion Paper for the

National Grass Seed Action Plan

2013 to 2015

(2 years)

Version 3

Contents

|  | Page |
| --- | --- |
| Call to Action | 2 |
| Plan for 2013 | 2 |
| Background – Journey to 2012 | 2 |
| Background – 2012 to today, MLA Grass seed Resources and Processor/Supermarket Survey | 2 |
| Key Components / Strategies to a National Grass Seed Action Plan | 5 |
| - National Grass Seed Leadership Group | 5 |
| - National Communications Program | 5 |
| - Resources | 6 |
| - Cost of Seed Calculator | 6 |
| - Carcase seed assessment, animal information and feedback | 6 |
| - Positive pathways for seed infested lambs | 7 |
| - Complimentary Research, Development and Extension | 8 |
| - Winning Against Seeds Producer Workshops | 8 |
| - MLA Producer Demonstration Sites (PDS) | 9 |
| - Trial Seed Kills | 9 |
| - Measurable targets / milestones | 10 |
| - Indicative stakeholder / co-investor engagement strategy | 11 |
| - Indicative budget / funding summary | 12 |

Discussion Paper for the National Grass Seed Action Plan

2013 to 2015 (2 years)

Call to Action

Grass seed infestation of carcases continues to be the biggest single issue facing the “whole supply chain” of the Australian prime lamb industry (and in some cases sheepmeat); encompassing significant losses and frustrations from  – producers, livestock agents, lamb and skin processors, wholesalers and retailers.  Many companies from these sectors have indicated that the time is right for the whole industry to focus their resources in a united action and work together to significantly reduce seed contamination.

Such desire is coming from producers and their State DPI’s and Research & Development Corporations (RDC’s), individual meat and skin processors and their RDC’s and /or Governing Councils, supermarkets, and the numerous service providers that are a critical link in achieving action and practice change on the ground.

Plan for 2013

| Date | Task/ activity | Responsibility |
| --- | --- | --- |
| April ‘13 (11 April ’13) (24 April ’13) | Teleconference of interested parties / drivers to determine aim and invitees to Industry Scoping Workshop (Current GSeed Resource Reference Group – MLA, RSSA, JBS, Coles, WAMMCO, ALPA, plus Vic DPI, NSW DPI, AMPC | RSSA |
| 30 May’13 | National Grass seed Action Plan Scoping Workshop Develop & commit to the National Action Plan (see below) | RSSA, MLA, AMPC |
| June ‘13 | Appoint National Coordinator and develop “Comms Plan” | Industry Reference Grp |
| July – Dec’13 | Deliver the nationally coordinated Grass Seed Action Plan | Everyone, plus National Coordinator |
| Feb ‘14 | Review and plan for 2014/15 | Industry Reference Grp |

Background

Even with an increase in direct on-farm purchases and increased feedback direct to producers, and in some cases financial penalties up to $1.50/kg DW, there are still signs of a lack of ownership of every sector’s contribution to the problem.

Processors carry a lot of the unseen losses in terms of reduced daily throughput, increased labour costs, an unhappy labour force, downgraded product, reduced meat yield and risk of market compensation claims.  Similarly, producers forego a loss of production potential and income from seed infestation in lambs.

Journey to 2012

In 2002, with national consultation, a suite of “Winning Against Seeds” resources was developed and published by MLA.  Prior to this, in the late 90’s, South Australia had a “Grass Seed Taskforce” in response to buyers threatening to move away from saleyards if the level of grass seed could not be reduced, declared or managed.

The SA Taskforce had some effect by:

- Bringing some key stakeholders to the one table, once per year to focus and plan

- Running some, but not enough workshops in “hot-spot” areas

- Running annual, timely, 4-6 week long media features just prior to the seed infestation period

- Encouraging “Trial Seed Kills” of individual producers lots of lambs

- Encouraged producers to visit the abattoir to observe theirs & others lambs

The lack of total industry participation, and the need for processors to focus on supply, rather than quality during the dry seasons, resulted in this Taskforce not delivering the intended outcomes.  However, they did learn lessons which can help today, in particular, that industry can work together on key issues.

The run of dry seasons / springs over a large area of Australia from 2005 – 2008 saw the grass seed problem decline, but the return to better springs has seen the grass seed issue return with a vengeance, with a greatly increased incidence of grass seed contamination of lambs.

2012 to today, MLA Grass seed Resources and Processor/ Supermarket Survey

The MLA Winning Against Seeds publications have  been reviewed and updated and will be a valuable tool in helping to educate producers and service providers about the problem and possible strategies to address it.

In 2012, as part of the MLA Winning Against Seeds resources review and upgrade, major processors and supermarkets were surveyed on the grass seed issue.  Survey participants slaughtered 80% of Australia’s lamb.

Businesses were asked to rate (on a scale of 1–5) how big a problem grass seeds are for the business.  All respondents, with the exception of two, rated the problem 4 or 5, or a major problem, with the majority scoring five.  Many respondents indicated they felt “grass seed was the number one problem facing their business.”

Further salient and emotional comments and findings included the likes of:

Timing

“Grass seed is a problem in the works for nine months of the year, but the problem is generated over a period of two months on farm.  There is a need to really ramp up awareness leading into the two month period when seed is set.”

Impact - Cost

“Seeds are a huge problem – single biggest issue.”

“In NSW, possibly, on average, 30-40% of all mobs consigned have a seed problem, acknowledging that this is little during the “sucker season” for three months of the year, and more in the carry-over lambs during the other nine months.

“Estimates of the percentages of lamb carcases requiring trimming during high risk periods ranged between 10% and 60%, with three works (with total annual lamb kill of 2.6 million) estimating at least 50%.”

Not all survey respondents were able to supply an estimate of the costs of seeds to their business.  The estimates from those that did varied between $10 to $20 per carcase and up to $30 for heavily affected carcases. (ie $1.00 to $1.50kg DW).  A service works estimated that it costs them an extra $4-$5 per carcase.  It is quite a challenging exercise to establish the costs to the processing business of grass seeds.  Factors that have to be taken into account and costed (in order of importance as reported by processors) include:

- Extra labour costs of trimming

- Slower chain speed

- Loss of meat value

- Potential loss of export licence

- Decreased skin value

- Potential damage to relationships with suppliers and customers

- Low staff morale.

“Get quite low morale on the kill floor when get seedy lambs through because of the amount of trim and wastage and how tedious trimming can be.”

As a result of this finding, MLA is currently developing a project to better define the post-farm gate impact of grass seeds and develop a methodology by which processors can customise the estimation for their own situation.

Carcase Information and Feedback

“All but two of the processors responding to the survey were happy to be involved in a campaign of producer and agent education.  One of those not interested in being involved had rated the problem for their works as only a 2 out of 5.”

“Processors have let their clients (including producers) down because they are not consistent with how they report the issue. A producer’s sheep will get reported at one works and not another – need to get seed reporting consistent across works.”

“Need to get more information out to producers and/or get producers through the works to see the carcases.”

A National Grass Seed Action Plan

“The majority of processors considered that producer awareness and education was an essential strategy for addressing the problem.  This includes increasing their understanding of the problems seeds cause.”

Key Components / Strategies to a National Grass Seed Action Plan

# National Grass Seed Leadership Group

- Membership from processors, retailers, producers, industry bodies, service providers

- Convene / host the Inaugural “National Grass Seed Action Plan Scoping Workshop” for all interested parties and co-investors (May 2013)

- Meetings:

  - Face to face once per year – set strategy

  - Teleconference, 2-3 times per year

- Appoint National Coordinator,

  - Proposed that in the interim, Anne Collins, RSSA, coordinate the National Workshop

  - A Terms of Reference developed for National Coordinator, and advertised

  - Contracted jointly by MLA, AMPC.

  - Develop measurable targets

  - Develop investment plan

  - Engage all sectors, stakeholders

  - Identify and develop seasonal predictors of potential hot-spots

  - Develop & manage the communications plan.

  - Manage further RD&E developments

  - Coordination of training

  - Evaluation - (KASA – knowledge, attitudes, skills, aspirations, pre and post)

# National Communications Program

The National Coordinator, in conjunction with the Leadership Group will develop a national communications program that engages and empowers all key stakeholders to play their role and will include the likes of.

## The major platform will be a timely, 4-6 week major feature by media in each state involving the likes of:

- 2 page features of “Winning Against Seed” in 4 states (WA, SA, NSW, Vic, ?Tas)

- 2 page spread, 5 articles  ($2000 per page – recouped in aligned advertising)

- Media: Coords all the articles (on being given a list of targets)

  - In-kind preparation of the content or 5 articles x 5 weeks x 4 states = 100 articles.

## Identify target hot spots & the appropriate timing for communications

## Develop the Communications plan and “key messages” on which the plan will be assessed

## KASA telephone survey – pre/post

## Empower and enlighten the communications of all stakeholders and partners to play their role.

All stakeholders such as State DPIs’, processors, Livestock Agents, RDC’s with newsletters / email lists will be supported and encouraged to distribute timely grass seed messages, and develop special sections in their communications.

The National Communications Plan will focus on aspects of the whole Australian sheep industry – meat, skin and wool, as the losses, problems and solutions are applicable to both lamb and sheepmeat enterprises, as well as the wool enterprise.  The seed reduces the value of each product differently, but the on-farm issues are identical in lower growth rates of weaners and the associated ill-thrift, lower survival, lower tolerance to worm challenges, lower fleece weight of the most valuable fleece in the sheep’s life, lower reproduction rates, especially in maidens, and of course the impact on general animal welfare.

Specifically, both on-farm RDC’s, MLA and AWI, have significant communication mechanisms and support various state networks with extensive communication programs and they will be encouraged to participate.

# Resources

In 2012 the following resources were re-developed /updated and will be of great value for this Action Plan

- Booklet – Winning Against Seeds

- Tips & Tools – Winning Against Seeds

- Producer Workshop – PowerPoint & session plan(s)

- Awareness Poster

The option to produce a DVD for use at field days and training sessions, and for  mass distribution has also been suggested as a new resource requiring development.

Also the preservation of seed infested carcase / cuts will need to be explored so the damage can be demonstrated to all industry sectors (eg. Cryovac, resin blocks / moulds)

# Cost of Seed Calculator

Processors are aware of the significant costs to their business of seed contaminated carcases, but most are not able to quantify the true overall cost of handling seed infested lambs and its effect on profit margins.  This in turn makes it difficult to accurately quantify price penalties applied.  Currently there is a perception among producers that processors are taking advantage of them with the current seed penalties.  MLA is developing a project to thoroughly and independently study the additional costs and increased risk when processing seed damaged carcases, and from this study a simple calculator will be developed for other lamb (and sheepmeat) supply chains to use when addressing the same issue.

# Carcase Seed Assessment, Animal Information and Feedback Systems

Currently individual processors are using a variety of different formats when providing feedback on seeds to producers.  There is variation between works in how seed contamination is described and how and when penalties are applied.  This potentially causes confusion and consternation when producers may consign similar lambs to different works and get different information back regarding seeds.

There is a need and interest within the processing sector for:

- New carcase measurement technologies (AMPC / MLA)

- Further standardisation of feedback on seeds to producers

- Electronic data capture and auto transfer (a high interest of NSW and VIC DPI)

Integration of animal health and carcase disorders with the standard weight and fat feedback (a key platform of MLA’s Livestock Data Link (LDL) program – currently in pilot)

MLA has recently released Terms of Reference – Systematic review of technologies that can be applied to data capture and management within red meat supply chains – to review the potential technologies that can be applied to data capture and management in supply chains.

The RMCiC Lamb Supply Chain and Animal Information RD&E plan has a project focus area addressing animal health and carcase quality issues: “Use information technologies to collect, interpret, monitor and provide feedback on lamb carcasses throughout the supply chain”

This project will be developed in conjunction with the seed contamination and animal health issues in lamb and ewe carcasses.  The project will assist with the development of new integrated information feedback technologies, engage sheep producer case study farms and work across at least five supply chains.

Consideration should also be given to ensuring reporting through the National Sheep Health Monitoring Program run by Animal Health Australia is consistent with standard industry practice.

Also some consideration will need to be given to “skins” and what if any feedback can be given about them.

# Positive pathways for seed infested lambs

The National Action Plan is clearly focused on encouraging producers and livestock agents to determine via trial seeds kills and feedback, if lambs have seed before dispatching them to market or over the hooks.  When stock are found to be seed infested through this process, there must be some clearly developed pathways for sale of these stock, rather than forcing the producer to feel he must “hide and conceal” and market on a “buyer-beware” basis.

Assuming some management practices don’t effectively reduce the seed infestation of lambs every year, there must be some positive pathways developed and recognised for “seed infested” lambs.

In particular, a proportion of these lambs find their way to regional saleyards and domestic abattoirs.  So as to reduce the surprise element to whoever is receiving those lambs, whether slaughtered or back-grounded, various methods of communication and disclosure of the seed status need to be explored.

Some options may include:

- Verbal placarding at saleyards

- Prior to dispatch to processor, negotiation on price, delivery date/time, and number of lambs in the consignment with the processor

- Inclusion of “seed status” on the National Vendor Declaration (NVD)

- Inclusion of “seed status” on any sale agreement, ie producer to backgrounder/feedlotter, producer to processor.

Clearly there is currently a difference in the tolerance of seed between exporters and supermarkets who must sign zero foreign object declarations on consignments, compared to some domestic abattoirs who can manage some seed, “at a price”.  This is sending a mixed message to producers and will need to be considered.

# Complimentary Research, Development and Extension (RD&E)

Complimentary RD&E will be identified along all sectors of the supply chain. Some initial thoughts are:

On-farm – emerging grass problems

An opportunity is emerging to partner with the cropping industry RDC’s and Framing Systems Groups as early indications are that the shift to no-till farming systems, particularly in the lower rainfall, lighter sandy country, is leading to a significant increase to Brome grass populations.  As well as causing significant crop yield loss, there is also the increasing threat of greater infestation of the lambs which have traditionally grazed these stubbles just prior to slaughter or entry into feedlots.  In addition, the use of some herbicides are tending to develop strains of grasses that either have a staggered germination, or a later germination, which misses the normal spraying window, and allows the grass to flourish and set seed.

On-farm – Pastoral weaner survival

Many pastoralists experience greater loss of Merino weaners in the good years when after shearing in spring, the lambs are turned out into tall seedy grass.  Losses, although not quantified could be from flies, worms and severe grass seed infestation, with the latter being under estimated by most.  Those lambing in later winter and shearing in summer/autumn may lose the weaners before first shearing.

Whole of supply chain – at what rate does the seed dissolve, and what scar/tissue damage is left?

This is a question often asked, for which there is only anecdotal evidence that “once a lamb is infested it will need to become hogget or mutton before the seed is dissolved” and the skin will never make premium lamb-skin quality.  Although possibly difficult research to conduct with current Animal Ethics requirements, the rate of seed dissolving could be explored.

Whole of supply chain - mutton

Another question often asked is, “if pastoral lambs fill up with seed (which they might do every 1 in 8-10 years), why is there little sign of seed in mutton, or is there? Once again, another possible research question.

# Winning Against Seeds Producer Workshops

Ideally delivered through the Making More from Sheep (MMfS) network, the facilitated technical workshop currently focuses clearly on a management strategy –“a four-point plan”, with a clear outcome of attendees heading home with their own, clearly articulated action plan based on:

- Developing an awareness of the issue

- Determining the impact of grass seeds to the business

- Develop and implement an integrated grass seed management strategy

- Obtain feedback, monitor and review management strategy.

Deliverers and workshop organisers / hosts:

Facilitator - to bring learning together, and assist producers to make “own action plan”

Agronomic Session – in kind by stakeholder

Livestock Marketing – in kind by Livestock Agent.

Lamb and skin Processor / Retailer session – in kind by same (ideally include abattoir tour or  bring seed infested carcase)

Workshop format – very flexible

The workshop can be stand-alone half day or combined with something else such as:

- Meat Standards Australia (Lamb)

- Enhanced Abattoir Surveillance (EAS) program (SA only)

- Animal Health & Disease Workshops

Partner with processor, agronomist, agent and/or saleyard operator

Facilitated discussion

PowerPoint and various session plans available

Other resources – Booklet, Tip & Tool

Possible funding Model:   $2000, 20 persons, (MMfS: $1000, Producers - $50ea).

Target number of workshops (tbc) could be SA (5), NSW (15), VIC (10), WA (5), QLD/TAS (tbc).

Over time, consideration will be given to “e-extension” delivery methods via the web, etc.

Sectors that could be encouraged to participate in these workshops with producers include Livestock Agents and Rural Merchandisers, the MLA NLRS (National Livestock Reporting Service)

# MLA Producer Demonstration Sites (PDS)

MLA's Producer Demonstration Sites (PDS) program supports producer groups and consultants to demonstrate, develop and adopt MLA research findings and technologies as well as seek research and development solutions to on-farm problems.  Through the PDS program, producers are provided with a practical, hands-on environment, and with the rigor of a research / business plan that enables them to share experiences and participate in the commercial application of research outputs in the following areas:

- Pasture and grazing management (southern projects)

- Weed management

- Improving liveweight gain

- Improving reproductive performance

- Animal health and welfare

- Enhancing enterprise efficiency

The National Grass Seed Action plan will be enhanced and assisted by PDS’s across the nation to provide local learning and the opportunity to drive State and national communication opportunities.  At least six sites would be required nationally, NSW (2), Vic (2), and one each in SA and WA (?also Tas).

# Trial Seed Kills

All processors will be encouraged to offer a service of trial seed kills, and via media, workshops, MLA PDS’s and support from Livestock Agents, producers will be encouraged to take advantage of this valuable service.  Trial seed kills involve a portion of a consignment or mob randomly selected and sent for processing.  These animals are monitored closely through the slaughter process and assessed for grass seed contamination.  Feedback is then provided to the producer about the grass seed status of their stock.  The basic steps involved in a trial seed kill include:

- Contacting the processor to organise a trial kill (this can be done personally or through an agent)

- Randomly selecting up to 10% of lambs (or 20 min) from the mob

- Organising transportation to the processor

- Receiving feedback – generally within 24 hours

Other options, with a bit less rigor / reliability but possibly worthy of consideration when trading producer to feedlotter or situated a long distance from an abattoir is to:

- slaughter 3-4 lambs on-farm

- consign some lambs to the local regional abattoir / butcher.

# Measurable Targets / Milestones (example only)

Working together

Demonstration of total sectorial participation in this major whole of supply chain issue.

Identify the seasonal predictors of possible hot-spots to focus communications & engagement.

Impact

Eliminate any incidence of ‘high” seed in valuable loin cuts.

Decrease the incidence of “med & high” in the rump from XX% down to XX%

Resources

On-going development of a Cost of Seed Calculator, and use by other supply chain

Producer training

Run the following workshops, producer attendance targets and media awareness

|  | SA | NSW | VIC | WA | QLD | TAS | TOTAL |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Mill. Lambs slaughtered in 2012 | 3.68 | 4.79 | 9.05 | 1.65 | 0.311 | 0.53 | 20.0 |
| No. of Workshops | 5 | 15 | 10 | 5 | ? | ? | 40 |
| No of producers @ workshops | 100 | 300 | 200 | 100 | ? | ? | 750 |
| “e-Extension” workshops | ? | ? | ? | ? | ? | ? | ? |
| Trial Seed Kills | ?? | ?? | ?? | ?? | ?? | ?? | ??? |
| Media articles |  |  |  |  |  |  | 250 |
| Web strikes |  |  |  |  |  |  | ??? |
| Bulletins |  |  |  |  |  |  | ??? |
| Tip ‘n’ Tool |  |  |  |  |  |  | ???? |

# National Grass Seed Action Plan – Indicative Stakeholder / Co-Investor Engagement Strategy

| Strategy | MLA | AMPC | JBS | Coles | Thomas Foods | ALPA | WAMMCO | National Coordinator |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. National Reference Group Members & Coord | R Apps ( R&D) R Jeffrey ( Ext) | Fahri (tbc) | Dale Cameron | Dale Pemberton | (tbc) | Phil Nagel | R Davidson | Anne Collins (interim, tbc) |
| 2.National Comms Plan |  |  |  |  |  |  |  |  |
| 3.Resources | Bulletin, Tip n Tool Awareness Poster |  |  |  |  |  |  |  |
| 4.Cost of Seed Calculator | MLA (R&D) |  |  |  |  |  |  |  |
| 5.Carcase measurement, Animal Information & Feedback Systems | Standardise Feedback Data Capture Systems Enhanced Abb Surveil. Livestock Data Link |  |  |  |  |  |  |  |
| 6.Producer Workshops | MMfS |  |  |  |  |  |  |  |
| 7.MLA PDS’s | NSW 2, Vic 2, SA,WA |  |  |  |  |  |  |  |
| 8.Trial Seed Kills |  |  |  |  |  |  |  |  |

|  | Other Abbs | Woolworths | Landmark | Elders | RuralCo | Saleyards | Skins | SASAG / SIF |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| National Reference Group Members (cont) |  | D Hudson (tbc) |  |  |  | R James (tbc) | P Fitzsummons PKF (tbc) | L Fitzgerald (tbc) |
| National Comms Plan |  |  |  |  |  |  |  |  |
| Resources |  |  |  |  |  |  |  |  |
| Animal Info & F’back Sys |  |  |  |  |  |  |  |  |
| Producer Workshops |  |  |  |  |  |  |  |  |
| MLA PDS’s |  |  |  |  |  |  |  |  |
| Trial Seed Kills |  |  |  |  |  |  |  |  |

|  | NSW DPI | VIC DPI | SA | WA | TAS | QLD | AWI | Media |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| National Reference Group Members (cont) | A White (tbc) | P Bailey | F Spurling |  |  |  |  |  |
| MMfS State Coords | S Duff | L Kubeil | N Morley | J England | A Bailey | T Hamilton |  |  |
| National Comms Plan |  |  |  |  |  |  |  |  |
| Resources |  |  |  |  |  |  |  |  |
| Animal Info & F’back Sys |  |  |  |  |  |  |  |  |
| Workshops |  |  |  |  |  |  |  |  |
| MLA PDS’s |  |  |  |  |  |  |  |  |

# National Grass Seed Action Plan – Indicative Budget / Funding Summary ($000’s)

|  | TOTAL | MLA | AMPC | JBS | Coles | Thomas Foods | WAMMCO | ALPA | SASAG / PIRSA | Media | Other Abattoirs | Woolworths | Landmark | Elders | RuralCo | Saleyards | Skins | NSW DPI | VIC DPI | DAFWA | TAS / QLD | Producers |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Funds – cash (tbc) | 550 | 265 | 110 |  |  |  |  |  | 100 | 50 |  |  |  |  |  |  |  |  |  |  |  | 30 |
| Funds – in kind () | 400 *** |  | SCO | SCO |  | SCO |  |  |  |  |  |  |  |  |  |  |  | tbc | 200 |  |  |  |
| National Reference Group | 20 | 5 | 5 |  |  |  |  |  | 10 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| National (or State) Coordinator | 60 | 20 | 20 |  |  |  |  |  | 20 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| National Comms Plan | 65 |  |  |  |  |  |  |  | 15 | 50 |  |  |  |  |  |  |  |  |  |  |  |  |
| Resources Development | 20 | 10 | 10 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Cost of Seed Calculator | 60 | 30 | 30 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Animal Information & Feedback Sys | 510 | 40 | 40 |  |  |  |  |  | 30 |  |  |  |  |  |  |  |  | tbc | 200 |  |  |  |
| MMfS – Winning Against Seed Workshops | 80 | 40 |  |  |  |  |  |  | 10 |  |  |  |  |  |  |  |  |  |  |  |  | 30 |
| MLA PDS’s (6) | 135 | 120 |  |  |  |  |  |  | 15 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Trial Seed Kills |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

***	In this Action Plan, there is a huge in-kind, possibly in the order of 3:1 in relation to the “cash” – a reflection of the priority by many.

Eg. SCO – Supply Chain Officer (currently funded 50:50 with Sheep CRC)